## Sheet1
Bug ID | Bug Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Assigned To | Comments
BUG001 | Login Fails with Valid Credentials | User cannot log in even with valid credentials. | 1. Enter valid username. 2. Enter valid password. 3. Click 'Login'. | User should be redirected to the product page. | User remains on the login page with no error message. | High | High | Open | Developer A
BUG002 | Sorting by Price Not Working | Sorting products by price (low to high) does not work. | 1. Click the 'Sort' dropdown. 2. Select 'Price (low to high)'. | Products should be sorted by price in ascending order. | Products are not sorted correctly. | Medium | Medium | Open | Developer B
BUG003 | Product Details Not Displaying | Clicking on a product does not display its details. | 1. Click on a product. | Product details (name, description, price) should be displayed. | No details are shown. | High | High | Open | Developer C
BUG004 | Add to Cart Button Not Functional | 'Add to Cart' button does not add the product to the cart. | 1. Click 'Add to Cart' on a product. | Product should be added to the cart. | Product is not added to the cart. | High | High | Open | Developer A
BUG005 | Checkout Page Crashes | Checkout page crashes when user clicks 'Continue' after entering details. | 1. Add items to the cart. 2. Click 'Checkout'. 3. Enter name and postal code. 4. Click 'Continue'. | User should be redirected to the payment page. | Page crashes with an error message. | Critical | High | Open | Developer B
BUG006 | Order Confirmation Not Displayed | No confirmation message is displayed after completing an order. | 1. Complete the checkout process. 2. Click 'Finish' on the payment page. | Confirmation message should be displayed: 'Thank you for your order!' | No confirmation message is shown. | Medium | Medium | Open | Developer C
BUG007 | Sensitive Data Exposed in Console | Sensitive data (e.g., user details) is visible in the browser console. | 1. Open the browser console. 2. Check for sensitive data. | No sensitive data should be exposed in the console. | Sensitive data is visible in the console. | High | High | Open | Developer A
BUG008 | Website Not Responsive on Mobile | Website layout breaks on mobile devices. | 1. Open the website on a mobile device. | Website should be responsive and functional on mobile devices. | Layout is broken, and buttons are not clickable. | Medium | Medium | Open | Developer B
BUG009 | Logout Button Not Working | Clicking the 'Logout' button does not log the user out. | 1. Click on the menu. 2. Click 'Logout'. | User should be logged out and redirected to the login page. | User remains logged in. | High | High | Open | Developer C
BUG010 | Remove from Cart Not Functional | 'Remove' button in the cart does not remove the product. | 1. Add a product to the cart. 2. Click 'Remove' on the product in the cart. | Product should be removed from the cart. | Product remains in the cart. | Medium | Medium | Open | Developer A